## Albert Lewis
A | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/19 - 1/26 | 5 |  | 0.33 |  | 3
1/27 - 2/2 | 8 |  | 1.5 |  |  |  |  | 3 | 2 | 2 | 6
2/3 - 2/9 | 5 |  |  |  | 2 |  |  | 3
2/10 - 2/16 | 9.5 |  | 2.5 |  | 2 | 3 |  |  |  |  | 3
02/16/16 - 02/22/16
02/23/16 - 02/29/16
03/01/16 - 03/07/16
03/08/16 - 03/14/16 | 13 |  | 5+ | 0 - learning 3 - implementation 4 - test | 5 |  |  | 3 | 5
03/15/16 - 03/21/16 | 11 |  |  | 0 - learning (learing more Django framework 3 - implementation (implementing user story) 4 - test ( testing against user story) | 3 |  |  | 5 | 3
03/22/16 - 03/28/16 | 11 |  |  | 0 - learning (learing more Django framework 3 - implementation (implementing user story) 4 - test ( testing against user story) | 3 |  |  | 5 | 3
03/29/16 - 04/04/16 |  |  |  | 3 - implementation 0 - Learning 4 - testing | 3 |  |  | 3 | 3
04/05/16 - 04/11/16
04/12/16 - 04/18/16
04/19/16 - 04/25/16
04/26/16 - 05/02/16
05/03/16 - 05/09/16
05/10/16 - 05/16/16
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Ashutosh Singh
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 5 | 5 | 0 | 0 - learn node.js | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
01/26/16 - 02/01/16 | 5 | 4 | 1 | homework, fixed a bug on the project, learn django | 2 | 0 | 0 | 1 | 1 | 0 | 0
02/02/16 - 02/08/16 | 5 | 4 | 1 | 0- learm jquery 1 - code inspection 4 - tested what code was working and what not | 2 | 1 |  |  | 2
02/09/16 - 02/15/16 | 6 | 5 | 1 | 3 - fixing code to support windows developement machine 1 - picked up a user a =nd started working on it
02/16/16 - 02/22/16 | 5 | 5 | 1 | 0 - learn about how chat server works 3 - pushed code to github 4 - learning django unit test | 2 |  |  | 1 | 2
02/23/16 - 02/29/16 | 4 | 3 | 1 | Homework, fixed vm | 0 | [5 empty] | 3
03/01/16 - 03/07/16
03/08/16 - 03/14/16 | 5 | 5 | 1 | 2 - created slides for presentation 3 - fixed last moment bug for presentation 5 - meet with the team 3 - wrapped up mu user stories |  |  | 1 | 2 |  | 2
03/15/16 - 03/21/16 | 5 | 5 | 1 | 6 - lecture reading/ homework 4 - tested existing rest API of the website |  |  |  |  | 4 |  | 1
03/22/16 - 03/28/16 | 3 | 3 | 1 | 4 - tested the jquery code for chat app 6 - finished homework |  |  |  |  | 2 |  | 1
03/29/16 - 04/04/16 | 8 | 6 | 2 | 3 - fixed rest api 5 - communcated with the team and met them two times in the week |  |  |  | 4 |  | 2
04/05/16 - 04/11/16
04/12/16 - 04/18/16
04/19/16 - 04/25/16
04/26/16 - 05/02/16
05/03/16 - 05/09/16
05/10/16 - 05/16/16
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## William Baldoumas
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 6 | 5 | 1 | 3. Created VM with dev tools for group, homework readings, set up pivotal tracker account; | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0
01/26/16 - 02/01/16 | 5 | 4 | 1 | 0. learned how to setup additional tools on new VM 1. investigated what tools we needed for new VM 3. Created, exported, and uploaded new VM 5. Weekly meeting 6. Homework readings and paper | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0
02/02/16 - 02/08/16 | 9 | 8 | 1 | 0. learned how to do more Git functions and learned how codebase was setup. 1. Investigated changes needed to be done for assigned tickets 3. Cloned repo and created needed branches for tickets 5. Weekly meeting 6. Homework readings, etc. | 2 | 1 | 0 | 1 | 0 | 1 | 3 | 0 | 0
02/09/16 - 02/15/16 | 12 | 11 | 1 | 0. learned more of the webapps structure and how our inheritence from Django is working 2. Designed and planned how code for password restriction ticket would need to be implemented 3. Made code changes needed for password restriction ticket 4. Tested above code changes with various password attempts. 5. Weekly meeting 6. Homework readings, etc. | 2 | 0 | 2 | 3 | 1 | 1 | 2
02/16/16 - 02/22/16 | 8.5 | 7.5 | 1 | 0. Grepped through the codebase to find how the templates were working in order to edit them 2. Came up with new text for the website, fixing many of the grammar issues 3. Made code changes needed for grammar cleanup ticket 4. Tested above code changes on various pages of the webapp 5. Weekly meeting 6. Homework readings, user story brainstorming | 2 | 0 | 1 | 2 | 0.5 | 1 | 1
02/23/16 - 02/29/16 | 6 | 5 | 1 | 0 & 1: learned about documentation tools and researched them 5. Weekly meeting 6. Homework & lecture readings | 2 | 2 | 0 | 0 | 0 | 1 | 1
03/01/16 - 03/07/16 |  |  |  | SPRING BREAK
03/08/16 - 03/14/16 |  | 9 | 1 | 0 & 1: learned about documentation tools and researched them 3. Implemented use of admindocs for Django documentation 5. Weekly meeting/prepping for presentation 6. Homework & lecture readings | 3 | 3 | 0 | 1 | 0 | 1 | 2
03/15/16 - 03/21/16 | 8 | 7 | 1 | 0 & 1: learned more about admindocs for Django documentation and looked into how best to implement the documentation for our tool. 5. General meetings, slack communication, weekly meeting. 6. Homework and readings | 2 | 2 | 0 | 0 | 0 | 1 | 2
03/22/16 - 03/28/16 | 10 | 9 | 1 | 0 & 1: Researced documentation tools for our JS files. 3. Worked more on documentation branch. 5. Slack communication. 6. Homework and readings | 2 | 2 | 0 | 2 | 0 | 1 | 2
03/29/16 - 04/04/16 | 7 | 6 | 1 | 0 & 1: Researced JSDoc and its use, planned email verification. 3. Worked on email verification and front end validations for email during registration 5. General meetings, slack communication, weekly meeting. | 1 | 2 | 0 | 3 | 0 | 1 | 0
04/05/16 - 04/11/16
04/12/16 - 04/18/16
04/19/16 - 04/25/16
04/26/16 - 05/02/16
05/03/16 - 05/09/16
05/10/16 - 05/16/16
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Oliver Nowak
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified 7 - homework | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 8.5 | 8 | 0.5 | 0: getting the app to run; 1: added user stories to pivotal tracker; 5: emails to team, helping team debug app startup issues, coordination with niall 7: reading homework material | 3.5 | 0.5 | 0 | 0 | 0 | 3 | 0 | 1
01/26/16 - 02/01/16 | 6 | 4 | 2 | 3: created VM with dev tools; fixed console errors for chat tool 7: reading homework material; homework paper | 0 |  |  | 3 |  |  |  | 1
02/02/16 - 02/08/16 | 3.25 | 2.25 | 1 | 0: code architecture inspection 3: merge Team-2 code into master; update README and gitignore, and create PR for Team-2 4: test merged changes 5: communicate to team about Team-2 code merge; filled out SPPP | 0.5 |  |  | 0.5 | 0.5 | 0.75
02/09/16 - 02/15/16 | 3 | 2 | 1 | 3: worked on navigation in chat tool; 5: created User Stories; talking to Niall about user stories |  |  |  | 1 |  | 1
02/16/16 - 02/22/16 | 5 | 3.5 | 1.5 | 1:1 with Emily 1: new user stories 3: documentation (see PR's) 5: emily VM; trouble-shooting team-member git issues; niall leaving |  | 0.5 |  | 1.5 |  | 1.5
02/23/16 - 02/29/16 | 5.5 | 5.5 |  | 3: fixing broken tests and selenium documentation 5: team communication/code reviews 7: homework #2 |  |  |  | 1.5 |  | 0.5 |  | 3.5
03/01/16 - 03/07/16 | 0 | 0
03/08/16 - 03/14/16 | 7 | 7 |  | 3: getting selenium tests to pass |  |  |  | 7
03/15/16 - 03/21/16 | 4 | 4 |  | 3: light documentation 5: helping son on his user story; answering questions from team |  |  |  | 1 |  | 3
03/22/16 - 03/28/16 | 5.75 | 5.75 |  | 5: answering userstory questions; PR merges; 7: homework | [5 empty] | 0.75 |  | 5
03/29/16 - 04/04/16 | 8 | 8 |  | 3: chat client arch document; generate ERD; create chat app state summary; fix and segregate selenium tests; 5: slides |  |  |  | 6 |  | 2
04/05/16 - 04/11/16 | 1.5 | 1.5 |  | 5: branch management, merge PR's | [5 empty] | 1.5
04/12/16 - 04/18/16 | 5.5 | 5.5 |  | 3: deployment; 5: scrum, user story guidance, organizing next sprint, PR Code reviews |  |  |  | 3.5 | 1 | 1
04/19/16 - 04/25/16 | 7.75 | 7.75 |  | 3: code-review PR's, merge PR's, deployment to production; fixing app errors as a result of last PR merge; 5: issue triage, and team organization around final presentation, create bugs |  |  |  | 6.75 |  | 1
04/26/16 - 05/02/16 | 2 | 2 |  | 3: slides, last minute deployment |  |  |  | 2
05/03/16 - 05/09/16 | 0 | 0
05/10/16 - 05/16/16 | 0 | 0
05/17/16 - 05/23/16 | 0 | 0
05/24/16 - 05/30/16 | 0 | 0
05/31/16 - 06/06/16 | 0 | 0
06/07/16 - 06/13/16 | 0 | 0
06/14/16 - 06/20/16 | 0 | 0
06/21/16 - 06/27/16 | 0 | 0
06/28/16 - 07/04/16 | 0 | 0
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Mike Trinh
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 4 | 4 | 0 | 0 - Learning Node JS, GitHub and installing Project | 3.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
01/26/16 - 02/01/16 | 4 | 2 | 2 | 0 - Learning Node JS | 1.5 |  |  |  |  | 0.5
02/02/16 - 02/08/16 | 5 | 4 | 1 | 0 - Learning Node JS. 1 - Determining requirements. 5 - Working on SPPP | 1 | 1.5 |  | 0.5 |  | 1
02/09/16 - 02/15/16 | 6 | 5 | 1 | 0 - Trying to understand the existing code that the previous group had implemented. 3 - Created triggers in sqlite database to delete messages older than 30 days or the oldest message when comments exceed 1000. 5 - Updated PivotalTracker 5 - Last adjustments to SPPP | 4 |  |  | 0.5 |  | 0.5
02/16/16 - 02/22/16 | 8 | 7 | 1 | 0 - Learned about how to create a SQL trigger within the Python code; learned about how to create Python tests 3 - Implemented code in models to check if a room has more than 5000 messages, deleting the old ones if it does 4 - Created unit test for the function | 4.5 |  |  | 1.5 | 1
02/23/16 - 02/29/16 | 7 | 5 | 2 | 0 - Learned about how to make a more efficient query to the database 3 - Implemented more efficient query 5 - Prepared for subteam meeting | 4 |  |  | 0.5 |  | 0.5
03/01/16 - 03/07/16 | 7 | 6 | 1 | 0 - Tried to understand how existing Javascript works and how it communicates with the Django; learned about views and serializers in Django | 6
03/08/16 - 03/14/16 | 10 | 8.5 | 1.5 | 0 - Learned about how to use Javascript to make a request that Python views would recognize 3 - Implemented backend code to change team name 5 - Worked on SDD | 4 |  |  | 3.5 |  | 1
03/15/16 - 03/21/16 | 5 | 2 | 3 | 0 - Learned about how to use JavaScript to change the appearance of elements in the website | 2
03/22/16 - 03/28/16 | 8.5 | 7.5 | 1 | 3 - Added a creator field in Room model. Adjusted the existing code to accommodate the change 5 - Talked with team about their user stories |  |  |  | 7 |  | 0.5
03/29/16 - 04/04/16 | 7 | 4 | 3 | 3 - Integrated back end implementation with Emily's front end work. Implemented immediate changes ot UI without having to reload the page after a room is changed 4 - Manually tested new changes |  |  |  | 3 | 1
04/05/16 - 04/11/16 | 0 | 0
04/12/16 - 04/18/16 | 0 | 0
04/19/16 - 04/25/16 | 0 | 0
04/26/16 - 05/02/16 | 0 | 0
05/03/16 - 05/09/16 | 0 | 0
05/10/16 - 05/16/16 | 0 | 0
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Hanhan Song
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 4 | 3 | 2 | 0: getting the app to run; 1: learning pivotal tracker; 5: team meetign and app startup issues 6: reading homework material | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0
01/26/16 - 02/01/16 | 4 | 2 | 2 | Setup git repo and virtual machine. Think about features to be implemented. | 1 | 0.5 | 0.5 |  |  | 2
02/02/16 - 02/08/16 | 4 | 3 | 1 | 0 - learn more about QA processes in Scrum development method 5. Weekly meeting 6. Homework readings and paper 6 - create documentation for QA in SPPP(metric, review, testing, and defect management) | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0
02/09/16 - 02/15/16 | 3 | 2 | 1 | 0 - code dive and learn more about the current code structure 1 - review current requirements and selected an user story to work on 5. Weekly meeting 6. Homework readings and paper | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
02/16/16 - 02/22/16 | 4 | 3 | 1 | 0 - learn about Django and node js framework 3 - revise the github instructions to set up the application 5. Weekly meeting 6. Homework readings and paper 6. Presentation during class | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0
02/23/16 - 02/29/16 | 6 | 5 | 1 | 0 - learn about websocket and socket.io for NodeJS 3 - fix the duplicate messages bug 5. Weekly meeting 6. Homework readings and paper | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 0
03/01/16 - 03/07/16 | SPRING RECESS |  |  |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
03/08/16 - 03/14/16 | 4 | 4 | 2 | 3 - fix the duplicate messages bug 5. Weekly meeting 6. Homework readings and paper | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
03/15/16 - 03/21/16 | 3 | 3 | 4 | 4. Learn Django and work on room selection with Ashu and Son 5. Weekly meeting 6. Homework readings and paper 6. Presentation during class |  |  |  | 1 |  |  | 3
03/22/16 - 03/28/16 | 3 | 3 | 4 | 4. Learn Django and work on room selection with Ashu and Son 5. Weekly meeting 6. Homework readings and paper |  |  |  | 1 |  |  | 3
03/29/16 - 04/04/16 | 3 | 3 | 4 | 4. Learn Django and work on room selection with Ashu and Son 5. Weekly meeting 6. Homework readings and paper |  |  |  | 1 |  |  | 3
04/05/16 - 04/11/16
04/12/16 - 04/18/16
04/19/16 - 04/25/16

## Son Nguyen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 4 | 3 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0
01/26/16 - 02/01/16 | 4 | 2 | 2 | Setup git, development envirnoment. Learned and revised django and javascript. Think about features to be implemented. | 1 | 0.5 | 0.5 |  |  | 2 |  | 0
02/02/16 - 02/08/16 | 4 | 3 | 1 | 0 - learn more about QA processes in Scrum development method 6 - create documentation for QA in SPPP(metric, review, testing, and defect management) | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0
02/09/16 - 02/15/16 | 3 | 2 | 1 | 0 - code dive and learn more about the current code structure 1 - review current requirements and selected an user story to work on | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
02/16/16 - 02/22/16 | 6 | 5 | 1 | 0 - learn about Ajax and node js framework 3 - implement the button UI and pop up for the invite to chat room button | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0
02/23/16 - 02/29/16 | 5 | 4 | 1 | 0 - learn about the verification process for email 3 - implement the backend for email verification for the invite to chat room | 2 | 0 | 0 | 2 | 0 |  | 0 | 0
03/01/16 - 03/07/16 | 3 | 3 | 0 | 3 - continuous implementation on the email verification | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
03/08/16 - 03/14/16 | 7 | 4 | 3 | 5 - meeting with Oliver to work out the problem regarding invite to private room which is not possible with the current room design 1 - Update the send email requirement into sending email in general (for changing password, send invites, etc | 0 | 1 | 0 | 3 |  | 3 | 0 | 0
03/15/16 - 03/21/16 | 5 | 4 | 1 | 0 - Learn about REST api and its implementation 2 - designing the REST api for the web app | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 0
03/22/16 - 03/28/16 | 6.5 | 4 | 2.5 | 3 - Implement the gatherMetric feature, and create a pull request for it 5 - Meeting with subteam 3a to decide about how to proceed with the RestAPI and its design 0 - Learn about restAPI in django and some related packages | 1.5 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0
03/29/16 - 04/04/16 | 8.5 | 5 | 3.5 | 5 - work with subteam3a to design and implement the RestAPI 3 - implement the restAPI 3 - implement script to automate the metric gathering process 3 - create comparison metric | 0 | 0 | 0 | 5 | 0 | 3.5 | 0 | 0
04/05/16 - 04/11/16 | 7 | 4 | 3 | 3 - implement userrroom table, and auto-increment userrroom table for easier jquery 5 - work with the present team to prepare for the presentation 5 - meet with subteam 3a to decide how to implement the API into the communication app, split up the work, I will increment the userroom table and how to auto increment, Ashu and Michael will implement the jquery. | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0
04/12/16 - 04/18/16 | 7 | 2 | 5 | 3 - Fix pull request and help teammates with sending email from Django 5 - Pair programming with team 3a to finalize the scalable working RestAPI. Make the chatApp message load reduce from O(mn) to O(1). | 0 | 0 | 2 | 0 | 0 | 5 | 0 | 0
04/19/16 - 04/25/16 | 7 | 5 | 2 | 3 - work on core documentation that we used for slides, so that everyone can work on the slide in the same pace. 3 - work on the presentation slide 4 - review pull requests, look at bugs introduced 5 - meet with team to synchronize our presentation | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0
04/26/16 - 05/02/16
05/03/16 - 05/09/16
05/10/16 - 05/16/16
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Emily Birmingham
| Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/16 - 01/25/16 | 0.5 | 0.5 | 0 | 0- learning slack, installing git, etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01/26/16 - 02/01/16 | 3 | 1 | 2 | 0- learning/installing VM | 1
02/02/16 - 02/08/16 | 3.5 | 2.5 | 1 | 0- learning code standards for JavaScript 6- worked on SPPP | 2 | [5 empty] | 0.5
02/09/16 - 02/15/16 | 3 | 2 | 1 | 6- leaning VM, working out problems with VM | [6 empty] | 2
02/16/16 - 02/22/16
02/23/16 - 02/29/16
03/01/16 - 03/07/16
03/08/16 - 03/14/16
03/15/16 - 03/21/16
03/22/16 - 03/28/16 | 6 | 4 | 2 | 6 - working on user story, edit and delete. HTML
03/29/16 - 04/04/16 | 6.5 | 3 | 3.5 | 5 - planning for presentation, 6 | [5 empty] | 1 | 5.5
04/05/16 - 04/11/16
04/12/16 - 04/18/16
04/19/16 - 04/25/16
04/26/16 - 05/02/16
05/03/16 - 05/09/16
05/10/16 - 05/16/16
05/17/16 - 05/23/16
05/24/16 - 05/30/16
05/31/16 - 06/06/16
06/07/16 - 06/13/16
06/14/16 - 06/20/16
06/21/16 - 06/27/16
06/28/16 - 07/04/16
07/05/16 - 07/11/16
07/12/16 - 07/18/16
07/19/16 - 07/25/16
07/26/16 - 08/01/16
08/02/16 - 08/08/16

## Betsy Berkey
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/19/17 - 01/25/17 | 5.63 | 5.3 | 0.33 |  | 5 |  |  |  |  | 0.3 |  | Get fully set up - github, pivotal tracker and slack | 5.63
01/26/17 - 02/01/17 | 6.5 | 5 | 1.5 |  | 3 | 2 | [5 empty] | Self learn Django | 6.5
02/02/17 - 02/08/17 | 10.5 | 9 | 1.5 |  | 8 | 1 | [5 empty] | Presentation slide deck and SPPP completed | 10.5
02/09/17 - 02/15/17 | 8.5 | 7 | 1.5 |  | 1 | 6 | [5 empty] | Start implementation; Switched to team 3, get fully set up again | 8.5
02/16/17 - 02/22/17 | 8 | 7 | 1 | Switched to Team 3 | 2 | [5 empty] | 5 | Learn git on Treehouse | 8
02/23/17 - 03/1/17 | 5 | 5 |  |  | 5 | [6 empty] | Implement front-end styling | 5
03/02/17 - 03/08/17 | 9 | 8 | 1 |  | 1 |  |  | 6 |  | 1 |  | Continue styling; work on SDD | 9
03/09/17 - 03/15/17 | 13.95 | 13.5 | 0.45 |  | 3 |  |  | 10 | 0.5 |  |  | Learn treehouse course for authentication and authorization | 13.95
03/16/17 - 03/22/17 | 4.45 | 4 | 0.45 |  | 1 |  |  | 3 |  |  |  | Start implementation for password reset | 4.45
03/23/17 - 03/29/17 | 5.3 | 5 | 0.3 |  | 4 |  |  | 1 |  |  |  | django authentication | 5.3
03/30/17 - 04/05/17 | 8.55 | 7.8 | 0.75 |  | 4 |  |  | 3.3 |  | 0.5 |  | Finish password reset feature | 8.55
04/06/17 - 04/12/17 | 4.25 | 3.5 | 0.75 |  | 0.5 |  |  | 3 |  |  |  | Redo password_resset - thought had to include all code but its a django installed app | 4.25
04/13/17 - 04/19/17 | 11.75 | 10 | 1.75 |  |  |  |  | 10 |  |  |  | Last iteration presentation | 11.75
04/20/17 - 04/26/17 | 7.5 | 7 | 0.5 |  |  |  |  | 6 |  | 1
04/27/17 - 05/03/17